## Sheet1
Jyothy Institute of Technology Project Work Breakdown Structure
Project Title: ESPOIR[Emerging Societal Problems Organised and Immediately Resolved]
DATE | Hamsa J | Sahana A | Sanjana S A | V Anagha Tiru
2016-07-13 | Ionic Framework installation |  | Ionic Framework installation | Ionic Framework installation
2016-07-14 | Ionic Framework installation... |  | Ionic Framework installation... | Ionic Framework installation...
2016-07-15 | Ionic Framework installation... |  | Ionic Framework installation... | Ionic Framework installation...
2016-07-16 | Ionic Framework installation... |  | Ionic Framework installation... | Ionic Framework installation...
2016-07-17 | Sunday
2016-07-18 | Building basic Blank App using Ionic Framework |  | Building basic Tabs App using Ionic Framework | Building basic Side Menu App using Ionic Framework
2016-07-19 | Building basic Blank App using Ionic Framework... |  | Building basic Tabs App using Ionic Framework... | Building basic Side Menu App using Ionic Framework...
2016-07-20 | Building basic Blank App using Ionic Framework... |  | Building basic Tabs App using Ionic Framework... | Building basic Side Menu App using Ionic Framework...
2016-07-21 | Building basic Blank App using Ionic Framework... |  | Building basic Tabs App using Ionic Framework... | Building basic Side Menu App using Ionic Framework...
2016-07-22 | Building basic Blank App using Ionic Framework... |  | Building basic Tabs App using Ionic Framework... | Building basic Side Menu App using Ionic Framework...
2016-07-23 | Guide Meeting
2016-07-24 | Sunday
2016-07-25 | Building app using Android Studio |  | Installing BBMP Sahaya App | Building basic Side Menu App using Ionic Framework...
2016-07-26 | Building app using Android Studio... |  | Making List of 4th row in app | Installing BBMP Sahaya App
2016-07-27 | Building app using Android Studio... |  | Making List of 4th row in app... | Making List of 3rd row in app
2016-07-28 | Installing BBMP Sahaya App |  | Registering 4 complaints using app | Making List of 3rd row in app...
2016-07-29 | Making List of 2nd row in app | Installing BBMP Sahaya App | Registering 4 complaints using app... | Registering 4 complaints using app
2016-07-30 | Making List of 2nd row in app... | Making List of 1st row in app | Registering 4 complaints using app... | Registering 4 complaints using app...
2016-07-31 | Sunday
2016-08-01 | Registering 4 complaints using app | Registering 4 complaints using app | Make a list of bugs and errors in the BBMP Sahaya App | Finding Bugs and errors in app
2016-08-02 | Registering 4 complaints using app... | Registering 4 complaints using app... | Make a list of bugs and errors in the BBMP Sahaya App... | Make a list of bugs and errors in the BBMP Sahaya App
2016-08-03 | Make a list of bugs in the BBMP Sahaya App | Make a list of bugs in the BBMP Sahaya App | Make a list of bugs and errors in the BBMP Sahaya App... | Make a list of bugs and errors in the BBMP Sahaya App...
2016-08-04 | Make a list of bugs in the BBMP Sahaya App... | Make a list of bugs in the BBMP Sahaya App... | Make a list of bugs and errors in the BBMP Sahaya App... | Make a list of bugs and errors in the BBMP Sahaya App...
2016-08-05 | Make a list of bugs in the BBMP Sahaya App... | Make a list of bugs in the BBMP Sahaya App... | Make a list of bugs and errors in the BBMP Sahaya App... | Make a list of bugs and errors in the BBMP Sahaya App...
2016-08-06 | Make a list of bugs in the BBMP Sahaya App... | Make a list of bugs in the BBMP Sahaya App... | Make a list of bugs and errors in the BBMP Sahaya App... | Make a list of bugs and errors in the BBMP Sahaya App...
2016-08-07 | Sunday
2016-08-08 | Installing Corona SDK | Installing Corona SDK | Installing Corona SDK | Installing Corona SDK
2016-08-09 | Installing Corona SDK... | Installing Corona SDK... | Installing Corona SDK... | Installing Corona SDK...
2016-08-10 | Guide Meeting
2016-08-11 | Working on creating various scenes -Corona Sdk | Working on Physics-Corona Sdk | Working on Events and Listeners- Corona Sdk | Working on Graphics-Corona Sdk
2016-08-12 | Working on creating various scenes -Corona Sdk... | Working on Physics-Corona Sdk... | Working on Events and Listeners- Corona Sdk... | Working on Graphics-Corona Sdk
2016-08-13 | Working on creating various scenes -Corona Sdk... | Working on Physics-Corona Sdk... | Working on Events and Listeners- Corona Sdk... | Working on Graphics-Corona Sdk
2016-08-14 | Sunday
2016-08-15 | Working on creating various scenes -Corona Sdk... | Working on Physics-Corona Sdk... | Working on Events and Listeners- Corona Sdk... | Working on Graphics-Corona Sdk
2016-08-16 | Working on creating various scenes -Corona Sdk... | Working on Physics-Corona Sdk... | Working on Events and Listeners- Corona Sdk... | Working on Graphics-Corona Sdk
2016-08-17 | Building Ilearn Science app using Corona Sdk | Building Let's Paint app using Corona Sdk | Building Ilearn Science app using Corona Sdk | Building Let's Paint app using Corona Sdk
2016-08-18 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk...
2016-08-19 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk...
2016-08-20 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk...
2016-08-21 | Sunday
2016-08-22 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk...
2016-08-23 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk...
2016-08-24 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk...
2016-08-25 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk...
2016-08-26 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk...
2016-08-27 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk...
2016-08-28 | Sunday
2016-08-29 | Preparing for internal examinations | Preparing for internal examinations | Preparing for internal examinations | Preparing for internal examinations
2016-08-30 | Preparing for internal examinations... | Preparing for internal examinations... | Preparing for internal examinations... | Preparing for internal examinations...
2016-08-31 | Preparing for internal examinations... | Preparing for internal examinations... | Preparing for internal examinations... | Preparing for internal examinations...
2016-09-01 | Internal Assesment
2016-09-02
2016-09-03
2016-09-04 | Sunday
2016-09-05 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Ilearn Science app using Corona Sdk...
2016-09-06 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Ilearn Science app using Corona Sdk...
2016-09-07 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Ilearn Science app using Corona Sdk...
2016-09-08 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Ilearn Science app using Corona Sdk...
2016-09-09 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Ilearn Science app using Corona Sdk...
2016-09-10 | Guide Meeting
2016-09-11 | Sunday
2016-09-12 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Ilearn Science app using Corona Sdk...
2016-09-13 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Ilearn Science app using Corona Sdk...
2016-09-14 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Ilearn Science app using Corona Sdk...
2016-09-15 | Guide Meeting
2016-09-16 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Ilearn Science app using Corona Sdk...
2016-09-17 | Building Ilearn Science app using Corona Sdk... | Building Let's Paint app using Corona Sdk... | Building Ilearn Science app using Corona Sdk... | Building Ilearn Science app using Corona Sdk...
2016-09-18 | Sunday
2016-09-19 | Make a list of features supported in project | Make a list of devices used and supported in project | Make a list of functional requirements for project | Make a list of non functional requirements
2016-09-20 | Make a list of features supported in project... | Make a list of devices used and supported in project... | Make a list of functional requirements for project... | Make a list of non functional requirements...
2016-09-21 | Make a list of features supported in project... | Make a list of devices used and supported in project... | Make a list of functional requirements for project... | Make a list of non functional requirements...
2016-09-22 | Make a list of features supported in project... | Make a list of devices used and supported in project... | Make a list of functional requirements for project... | Make a list of non functional requirements...
2016-09-23 | Make a list of features supported in project... | Make a list of devices used and supported in project... | Make a list of functional requirements for project... | Make a list of non functional requirements...
2016-09-24 | Guide Meeting
2016-09-25 | Sunday
2016-09-26 | Prepare Draft copy of features and devices | Prepare the Draft copy of Functional Requirements | Prepare draft copy of SRS Documentation | Prepare draft copy of non functional requirement
2016-09-27 | Prepare Draft copy of features and devices... | Prepare the Draft copy of Functional Requirements... | Prepare draft copy of SRS Documentation... | Prepare draft copy of non functional requirement...
2016-09-28 | Prepare Draft copy of features and devices... | Prepare the Draft copy of Functional Requirements... | Prepare draft copy of SRS Documentation... | Prepare draft copy of non functional requirement...
2016-09-29 | Prepare Draft copy of features and devices... | Prepare the Draft copy of Functional Requirements... | Prepare draft copy of SRS Documentation... | Prepare draft copy of non functional requirement...
2016-09-30 | Guide Meeting
2016-10-01
2016-10-02 | Sunday
2016-10-03 | SRS Specification and external source requirements | List Functional Requirement Specification | Work Breakdown Structure | SRS Description and design constraints
2016-10-04 | SRS Specification and external source requirements... | List Functional Requirement Specification ... | Work Breakdown Structure... | SRS Description and design constraints...
2016-10-05 | SRS Specification and external source requirements... | List Functional Requirement Specification ... | Work Breakdown Structure... | SRS Description and design constraints...
2016-10-06 | SRS Specification and external source requirements... | List Functional Requirement Specification ... | Work Breakdown Structure... | SRS Description and design constraints...
2016-10-07 | SRS Specification and external source requirements... | List Functional Requirement Specification ... | Work Breakdown Structure... | SRS Description and design constraints...
2016-10-08 | Guide Meeting
2016-10-09 | Sunday
2016-10-10 | Implementation of WBS in agile methodology | Abstract Design | SRS Editing | List non fuctional requirements for SRS
2016-10-11 | Implementation of WBS in agile methodology... | Abstract Design... | SRS Editing ... | List non fuctional requirements for SRS...
2016-10-12 | Implementation of WBS in agile methodology... | Abstract Design... | SRS Editing ... | List non fuctional requirements for SRS...
2016-10-13 | Implementation of WBS in agile methodology... | SRS Editing ... | SRS Editing ... | List non fuctional requirements for SRS...
2016-10-14 | Implementation of WBS in agile methodology... | SRS Editing ... | SRS Editing ... | List non fuctional requirements for SRS...
2016-10-15 | Implementation of WBS in agile methodology... | SRS Editing ... | SRS Editing ... | List non fuctional requirements for SRS...
2016-10-16 | Sunday
2016-10-17 | Create Github Account | Create Github Account | Create Github Account | Create Github Account
2016-10-18 | Learn hoe to use Github | Learn hoe to use Github | Learn hoe to use Github | Learn hoe to use Github
2016-10-19 | Create repository for project in Github | Upload Abstract on GitHub | Upload WBS on GitHub | Upload SRS on Github
2016-10-20 | Create repository for project in Github.... | Upload Abstract on GitHub... | Upload WBS on GitHub... | Upload SRS on Github...
2016-10-21 | Guide Meeting
2016-10-22 | Project Review
2016-10-23 | Sunday
2016-10-24 | Learning Lua Scene and Events | Learning to design app | Learning Lua Database management | Learning to create Widgets,GUI and maps
2016-10-25 | Learning Lua Scene and Events... | Learning to design app... | Learning Lua Database management... | Learning to create Widgets,GUI and maps...
2016-10-26 | Learning Lua Scene and Events... | Learning to design app... | Learning Lua Database management... | Learning to create Widgets,GUI and maps...
2016-10-27 | Learning Lua Scene and Events... | Learning to design app... | Learning Lua Database management... | Learning to create Widgets,GUI and maps...
2016-10-28 | Learning Lua Scene and Events... | Learning to design app... | Learning Lua Database management... | Learning to create Widgets,GUI and maps...
2016-10-29 | Learning Lua Scene and Events... | Learning to design app... | Learning Lua Database management... | Learning to create Widgets,GUI and maps...
2016-10-30 | Sunday
2016-10-31 | Design Sequence Diagram of the project | Design Block Diagram of the project | Design Database of project | Design Use Case diagram of the project
2016-11-01 | Design Sequence Diagram of the project... | Design Block Diagram of the project... | Design Database of project... | Design Use Case diagram of the project...
2016-11-02 | Design Sequence Diagram of the project... | Design Block Diagram of the project... | Build the ER Diagram of the project | Design Use Case diagram of the project...
2016-11-03 | Design Sequence Diagram of the project... | Design Block Diagram of the project... | Build the ER Diagram of the project... | Design Use Case diagram of the project...
2016-11-04 | Design Sequence Diagram of the project... | Design Block Diagram of the project... | Build the ER Diagram of the project... | Design Use Case diagram of the project...
2016-11-05 | Guide Meeting
2016-11-06 | Sunday
2016-11-07 | Uploaded Github with Sequence Diagram | Uploaded Block Diagram in GitHub | Uploaded ER diagram on Github | Uploaded Use Case Diagrams on Github
2016-11-08 | Write assignments and prepare for internals | Write assignments and prepare for internals | Write assignments and prepare for internals | Write assignments and prepare for internals
2016-11-09 | Write assignments and prepare for internals... | Write assignments and prepare for internals... | Write assignments and prepare for internals... | Write assignments and prepare for internals...
2016-11-10 | Write assignments and prepare for internals... | Write assignments and prepare for internals... | Write assignments and prepare for internals... | Write assignments and prepare for internals...
2016-11-11 | Write assignments and prepare for internals... | Write assignments and prepare for internals... | Write assignments and prepare for internals... | Write assignments and prepare for internals...
2016-11-12 | Write assignments and prepare for internals... | Write assignments and prepare for internals... | Write assignments and prepare for internals... | Write assignments and prepare for internals...
2016-11-13 | Sunday
2016-11-14 | Internal Assesment
2016-11-15
2016-11-16
2016-11-17 | Preparing for external examinations | Preparing for external examinations | Preparing for external examinations | Preparing for external examinations
2016-11-18 | Preparing for external examinations... | Preparing for external examinations... | Preparing for external examinations... | Preparing for external examinations...
2016-11-19 | Preparing for external examinations... | Preparing for external examinations... | Preparing for external examinations... | Preparing for external examinations...
2016-11-20 | Sunday
2016-11-21 | Preparing for external examinations... | Preparing for external examinations... | Preparing for external examinations... | Preparing for external examinations...
2016-11-22 | Preparing for external examinations... | Preparing for external examinations... | Preparing for external examinations... | Preparing for external examinations...
2016-11-23 | Preparing for external examinations... | Preparing for external examinations... | Preparing for external examinations... | Preparing for external examinations...
2016-11-24 | Preparing for external examinations... | Preparing for external examinations... | Preparing for external examinations... | Preparing for external examinations...
2016-11-25 | External Lab Exams
2016-11-26
2016-11-27
2016-11-28
2016-11-29
2016-11-30
2016-12-01 | Study Holidays
2016-12-02
2016-12-03
2016-12-04
2016-12-05
2016-12-06
2016-12-07
2016-12-08
2016-12-09
2016-12-10
2016-12-11
2016-12-12
2016-12-13
2016-12-14
2016-12-15
2016-12-16
2016-12-17
2016-12-18
2016-12-19 | External Theory Exam
2016-12-20
2016-12-21
2016-12-22
2016-12-23
2016-12-24
2016-12-25
2016-12-26
2016-12-27
2016-12-28
2016-12-29
2016-12-30
2016-12-31
2017-01-01
2017-01-02
2017-01-03
2017-01-04
2017-01-05
2017-01-06
2017-01-07
2017-01-08 | Sunday
2017-01-09 | Created a form as instructed by guide | Created a form as instructed by guide | Created a form as instructed by guide | Created a form as instructed by guide
2017-01-10 | Created a form as instructed by guide... | Created a form as instructed by guide... | Created a form as instructed by guide... | Created a form as instructed by guide...
2017-01-11 | Created a form as instructed by guide... | Created a form as instructed by guide... | Created a form as instructed by guide... | Created a form as instructed by guide...
2017-01-12 | Created a form as instructed by guide... | Created a form as instructed by guide... | Created a form as instructed by guide... | Created a form as instructed by guide...
2017-01-13 | Created a form as instructed by guide... | Created a form as instructed by guide... | Created a form as instructed by guide... | Created a form as instructed by guide...
2017-01-14 | Created a form as instructed by guide... | Created a form as instructed by guide... | Created a form as instructed by guide... | Created a form as instructed by guide...
2017-01-15 | Sunday
2017-01-16 | Guide Meeting
2017-01-17 | Study on support of database in corona | Study on control flow and events supported in Corona... | Made changes in ER diagram and database | Created login form for project
2017-01-18 | Study on support of database in corona... | Study on control flow and events supported in Corona... | Made changes in ER diagram and database... | Created login form for project...
2017-01-19 | Study on support of database in corona... | Study on control flow and events supported in Corona... | Made changes in ER diagram and database... | Created login form for project...
2017-01-20 | Study on support of database in corona... | Study on control flow and events supported in Corona... | Made changes in ER diagram and database... | Created login form for project...
2017-01-21 | Study on support of database in corona... | Study on control flow and events supported in Corona... | Made changes in ER diagram and database... | Created login form for project...
2017-01-22 | Sunday
2017-01-23
2017-01-24 | Guide Meeting
2017-01-25 | Study on fetching data from database in Corona | Study on control flow and events supported in Corona | Study on fetching data from database in Corona | Created sign up form for Project
2017-01-26 | Study on fetching data from database in Corona... | Study on control flow and events supported in Corona... | Study on fetching data from database in Corona... | Created sign up form for Project...
2017-01-27 | Study on fetching data from database in Corona... | Study on control flow and events supported in Corona... | Study on fetching data from database in Corona... | Created sign up form for Project...
2017-01-28 | Study on fetching data from database in Corona... | Study on control flow and events supported in Corona... | Study on fetching data from database in Corona... | Created sign up form for Project...
2017-01-29 | Sunday
2017-01-30 | Study on control flow and events supported in Corona | Study on control flow and events supported in Corona... | Study on support of database in corona | Created GUI for the project
2017-01-31 | Study on control flow and events supported in Corona... | Study on control flow and events supported in Corona... | Study on support of database in corona... | Created GUI for the project...
2017-02-01 | Study on control flow and events supported in Corona... | Study on control flow and events supported in Corona... | Study on support of database in corona... | Created GUI for the project...
2017-02-02 | Study on control flow and events supported in Corona... | Study on control flow and events supported in Corona... | Study on support of database in corona... | Created GUI for the project...
2017-02-03 | Study on control flow and events supported in Corona... | Study on control flow and events supported in Corona... | Study on support of database in corona... | Created GUI for the project...
2017-02-04 | Study on control flow and events supported in Corona... | Study on control flow and events supported in Corona... | Study on support of database in corona... | Created GUI for the project...
2017-02-05 | Sunday
2017-02-06 | Guide Meeting
2017-02-07 | Learns how to connect to Database and fetch information | Working on connecting forms and its functions | Creates database on remote server | Created GUI for the project
2017-02-08 | Learns how to connect to Database and fetch information... | Working on connecting forms and its functions... | Creates database on remote server... | Created GUI for the project...
2017-02-09 | Learns how to connect to Database and fetch information... | Working on connecting forms and its functions... | Creates database on remote server... | Created GUI for the project...
2017-02-10 | Learns how to connect to Database and fetch information... | Working on connecting forms and its functions... | Creates database on remote server... | Created GUI for the project...
2017-02-11 | Learns how to connect to Database and fetch information... | Working on connecting forms and its functions | Creates database on remote server... | Created GUI for the project...
2017-02-12 | Sunday |  |  | Created GUI for the project...
2017-02-13 | Guide Meeting
2017-02-14 | Create Database locally | Works on functionality of the project | Learning how to create local database | Created GUI for the project
2017-02-15 | Create Database locally... | Works on functionality of the project... | Learning how to create local database... | Created GUI for the project...
2017-02-16 | Create Database locally... | Works on functionality of the project... | Learning how to create local database... | Created GUI for the project...
2017-02-17 | Create Database locally... | Works on functionality of the project... | Learning how to create local database... | Created GUI for the project...
2017-02-18 | Create Database locally... | Works on functionality of the project... | Learning how to create local database... | Created GUI for the project...
2017-02-19 | Sunday
2017-02-20 | Guide Meeting
2017-02-21 | Working on connecting forms and its functions | prepared presentation for review process | Editing WBS and uploading in repository | Created GUI for the project...
2017-02-22 | Working on connecting forms and its functions... | prepared presentation for review process... | Editing WBS and uploading in repository... | Created GUI for the project...
2017-02-23 | Working on connecting forms and its functions... | prepared presentation for review process... | Editing WBS and uploading in repository... | Created GUI for the project...
2017-02-24 | Working on connecting forms and its functions... | prepared presentation for review process... | Editing WBS and uploading in repository... | Created GUI for the project...
2017-02-25 | Project Review
2017-02-26 | Sunday
2017-02-27
2017-02-28
2017-03-01
2017-03-02
2017-03-03
2017-03-04
2017-03-05 | Sunday
2017-03-06
2017-03-07
2017-03-08
2017-03-09
2017-03-10
2017-03-11
2017-03-12
2017-03-13
2017-03-14
2017-03-15
2017-03-16
2017-03-17
2017-03-18
2017-03-19
2017-03-20
2017-03-21
2017-03-22
2017-03-23
2017-03-24
2017-03-25
2017-03-26
2017-03-27
2017-03-28
2017-03-29
2017-03-30
2017-03-31
2017-04-01
2017-04-02
2017-04-03
2017-04-04
2017-04-05 | Target Date To Complete Draft Report
2017-04-06
2017-04-07
2017-04-08
2017-04-09
2017-04-10
2017-04-11
2017-04-12
2017-04-13
2017-04-14
2017-04-15 | Target Date To Complete Project 100%
2017-04-16
2017-04-17
2017-04-18
2017-04-19
2017-04-20
2017-04-21
2017-04-22
2017-04-23
2017-04-24
2017-04-25
2017-04-26
2017-04-27
2017-04-28
2017-04-29
2017-04-30
2017-05-01
2017-05-02
2017-05-03 | Target Date For Final Report
2017-05-04
2017-05-05
2017-05-06
2017-05-07
2017-05-08
2017-05-09
2017-05-10
2017-05-11
2017-05-12
2017-05-13
2017-05-14
2017-05-15